## Sprint 1
Task # | Sprint | Module Name | RCT.Id | Core Feature | Task Description | Start Date | End Date | % Progress | Task Owner
1 | S1 | 01. Establish User Control | 01.01 | User Management | Implement registered user role functionality | 2024-02-27 | 2024-03-02 | 100% | Vinay
2 | S1 | 01. Establish User Control | 01.01 | User Management | Implement guest role functionality | 2024-02-27 | 2024-03-02 | 100% | Likith
3 | S1 | 01. Establish User Control | 01.01 | User Management | Implement doctor role functionality | 2024-02-27 | 2024-03-02 | 100% | Afreen
4 | S1 | 01. Establish User Control | 01.01 | User Management | Implement Login for different users | 2024-02-27 | 2024-03-02 | 100% | Surekha
5 | S1 | 01. Establish User Control | 01.01 | User Management | Implement SignUp for different users | 2024-02-27 | 2024-03-02 | 100% | Vinay
6 | S1 | 01. Establish User Control | 01.01 | User Management | Create database for each user role | 2024-02-27 | 2024-03-02 | 100% | Venkat Reddy
7 | S1 | 01. Establish User Control | 01.01 | User Management | Create test cases for functionality | 2024-02-27 | 2024-03-02 | 100% | Balu Venkat
8 | S1 | 01. Establish User Control | 01.01 | User Management | Execute test cases and document the test execution log | 2024-02-27 | 2024-03-02 | 100% | Naresh
9 | S1 | 01. Implement Secure Authentication | 01.02 | User Management | Implement validation on fields to ensure accurate modifications: User Name is required and not null/blank | 2024-02-27 | 2024-03-02 | 100% | Vinay
10 | S1 | 01. Implement Secure Authentication | 01.02 | User Management | Implement validation on fields to ensure accurate modifications: Email Address is required and not null/blank | 2024-02-27 | 2024-03-02 | 100% | Likith
11 | S1 | 01. Implement Secure Authentication | 01.02 | User Management | Implement validation on fields to ensure accurate modifications: Password needs to meet validatoin criteria | 2024-02-27 | 2024-03-02 | 100% | Afreen
12 | S1 | 01. Implement Secure Authentication | 01.02 | User Management | Implement validation on fields to ensure accurate modifications: Phone number needs to meet validatoin criteria | 2024-02-27 | 2024-03-02 | 100% | Surekha
13 | S1 | 01. Implement Secure Authentication | 01.02 | User Management | Display whether the query of the account information was processed successfully. | 2024-02-27 | 2024-03-02 | 100% | Vinay
14 | S1 | 01. Implement Secure Authentication | 01.02 | User Management | Crosscut: FV - Field Validation Validations of fields mentioned in previous tasks are implemented | 2024-02-27 | 2024-03-02 | 100% | Likith
15 | S1 | 01. Implement Secure Authentication | 01.02 | User Management | Crosscut: Exception Handling Display error on invalid inputs and if unable to process submission | 2024-02-27 | 2024-03-02 | 100% | Afreen
16 | S1 | 01. Implement Secure Authentication | 01.02 | User Management | Implement Insert functionality for Sign up in each user database table | 2024-02-27 | 2024-03-02 | 100% | Arjun Reddy
17 | S1 | 01. Implement Secure Authentication | 01.02 | User Management | Create test cases for functionality | 2024-02-27 | 2024-03-02 | 100% | Balu Venkat
18 | S1 | 01. Implement Secure Authentication | 01.02 | User Management | Create test cases for validation | 2024-02-27 | 2024-03-02 | 100% | Naresh
19 | S1 | 01. Implement Secure Authentication | 01.02 | User Management | Execute test cases and document the test execution log | 2024-02-27 | 2024-03-02 | 100% | Balu Venkat
20 | S1 | 01. Manage Data | 01.03 | User Management | Update user dashboard design: Split each section(header, hero, info section,about section, contact section) | 2024-03-03 | 2024-03-07 | 100% | Afreen
21 | S1 | 01. Manage Data | 01.03 | User Management | Update user profile page design to be user friendly (Edit/Modify) | 2024-03-03 | 2024-03-07 | 100% | Surekha
22 | S1 | 01. Manage Data | 01.03 | User Management | Update fields such as Name, phone number, password | 2024-03-03 | 2024-03-07 | 100% | Vinay
23 | S1 | 01. Manage Data | 01.03 | User Management | Crosscuts: FV - Field Validation Build field criteria for modified fields | 2024-03-03 | 2024-03-07 | 100% | Likith
24 | S1 | 01. Manage Data | 01.03 | User Management | Crosscut: ET-Ex, User can edit their accounts only if they have logged in. | 2024-03-03 | 2024-03-07 | 100% | Surekha
25 | S1 | 01. Manage Data | 01.03 | User Management | Crosscut: Exception Handling - Display error message unable to access their profile. | 2024-03-03 | 2024-03-07 | 100% | Vinay
26 | S1 | 01. Manage Data | 01.03 | User Management | Implement the delete account functionality | 2024-03-03 | 2024-03-07 | 100% | Likith
27 | S1 | 01. Manage Data | 01.03 | User Management | Create a button to delete account | 2024-03-03 | 2024-03-07 | 100% | Surekha
28 | S1 | 01. Manage Data | 01.03 | User Management | Confirm the user's deletion decision | 2024-03-03 | 2024-03-07 | 100% | Vinay
29 | S1 | 01. Manage Data | 01.03 | User Management | Implement database functionality to update profile and delete account | 2024-03-03 | 2024-03-07 | 100% | Venkat Reddy
30 | S1 | 01. Manage Data | 01.03 | User Management | Implement logout functionality | 2024-03-03 | 2024-03-07 | 100% | Surekha
31 | S1 | 01. Manage Data | 01.03 | User Management | Create test cases for user readability | 2024-03-03 | 2024-03-07 | 100% | Naresh
32 | S1 | 01. Manage Data | 01.03 | User Management | Create test cases for functionality | 2024-03-03 | 2024-03-07 | 100% | Balu Venkat
33 | S1 | 01. Manage Data | 01.03 | User Management | Create test cases for validation | 2024-03-03 | 2024-03-07 | 100% | Naresh
34 | S1 | 01. Manage Data | 01.03 | User Management | Execute test cases and document the test execution log | 2024-03-03 | 2024-03-07 | 100% | Balu Venkat
35 | S1 | 01. Manage Account Recovery and Reset | 01.04 | User Management | Implement account recovery if user click on forgot password | 2024-03-03 | 2024-03-07 | 100% | Likith
36 | S1 | 01. Manage Account Recovery and Reset | 01.04 | User Management | Implement password reset link functionality while sending email | 2024-03-03 | 2024-03-07 | 100% | Vinay
37 | S1 | 01. Manage Account Recovery and Reset | 01.04 | User Management | Implement message on successful reset | 2024-03-03 | 2024-03-07 | 100% | Surekha
38 | S1 | 01. Manage Account Recovery and Reset | 01.04 | User Management | Crosscuts: FV - Field Validation, Check the email address validation | 2024-03-03 | 2024-03-07 | 100% | Afreen
39 | S1 | 01. Manage Account Recovery and Reset | 01.04 | User Management | Crosscut: Exception Handling - Display error message unable to reset password | 2024-03-03 | 2024-03-07 | 100% | Vinay
40 | S1 | 01. Manage Account Recovery and Reset | 01.04 | User Management | Create test cases for functionality | 2024-03-03 | 2024-03-07 | 100% | Balu Venkat
41 | S1 | 01. Send User Notification | 01.05 | User Management | Create test cases for validation | 2024-03-03 | 2024-03-07 | 100% | Naresh
42 | S1 | 01. Send User Notification | 01.05 | User Management | Execute test cases and document the test execution log | 2024-03-03 | 2024-03-07 | 100% | Naresh
43 | S1 | 01. Send User Notification | 01.05 | User Management | Implement email notification functionality to send notifications and password reset link | 2024-03-03 | 2024-03-07 | 100% | Likith
44 | S1 | 01. Send User Notification | 01.05 | User Management | Implement error messages/ notification functionality on each page | 2024-03-03 | 2024-03-07 | 100% | Surekha
45 | S1 | 01. Send User Notification | 01.05 | User Management | Crosscut: Exception Handling - Display error message unable to send notification | 2024-03-03 | 2024-03-07 | 100% | Afreen
46 | S1 | 01. Send User Notification | 01.05 | User Management | Create test cases for functionality | 2024-03-03 | 2024-03-07 | 100% | Balu Venkat
47 | S1 | 01. Send User Notification | 01.05 | User Management | Create test cases for validation | 2024-03-03 | 2024-03-07 | 100% | Balu Venkat
48 | S1 | 01. Send User Notification | 01.05 | User Management | Execute test cases and document the test execution log | 2024-03-03 | 2024-03-07 | 100% | Naresh

## Sprint 2
Task # | Sprint | Module Name | RCT.Id | Core Feature | Task Description | Start Date | End Date | % Progress | Task Owner
1 | S2 | 02. Appointment Management | 02.01 | Schedule Appointments | Implement a user interface for patients to select preferred appointment dates and times, select healthcare providers, and confirm appointment details | 2024-03-13 | 2024-03-18 | 85% | Vinay
2 | S2 | 02. Appointment Management | 02.01 | Schedule Appointments | Design a calendar view in the user interface displaying available appointment slots for the selected healthcare provider | 2024-03-13 | 2024-03-18 | 85% | Likith
3 | S2 | 02. Appointment Management | 02.01 | Schedule Appointments | Add a "Cancel Appointment" button to the user interface for patients to cancel their scheduled appointments | 2024-03-13 | 2024-03-18 | 85% | Surekha
4 | S2 | 02. Appointment Management | 02.01 | Schedule Appointments | Enable patients to reschedule appointments by providing options to select a new date and time through the user interface | 2024-03-13 | 2024-03-18 | 85% | Afreen
5 | S2 | 02. Appointment Management | 02.01 | Schedule Appointments | Verify that a patient can successfully schedule an appointment with a healthcare provider | 2024-03-13 | 2024-03-18 | 85% | Balu Venkat
6 | S2 | 02. Appointment Management | 02.01 | Schedule Appointments | Crosscut: ET-Ex, User can Schedule the appointements only if they have logged in. | 2024-03-13 | 2024-03-18 | 85% | Likith
7 | S2 | 02. Appointment Management | 02.01 | Schedule Appointments | Verify that a patient can cancel a scheduled appointment | 2024-03-13 | 2024-03-18 | 75% | Naresh
8 | S2 | 02. Appointment Management | 02.02 | Send Automated Reminders | Develop a user interface for healthcare providers to configure appointment reminder settings | 2024-03-19 | 2024-03-23 | 75% | Vinay
9 | S2 | 02. Appointment Management | 02.02 | Send Automated Reminders | Implement integration with communication channels (e.g., email, SMS) to enable automated delivery of appointment reminders | 2024-03-19 | 2024-03-23 | 75% | Likith
10 | S2 | 02. Appointment Management | 02.02 | Send Automated Reminders | Ensure that reminder messages are customized to include relevant appointment information and provider instructions | 2024-03-19 | 2024-03-23 | 75% | Surekha
11 | S2 | 02. Appointment Management | 02.02 | Send Automated Reminders | Implement encryption and data protection measures to maintain the confidentiality and security of reminder messages | 2024-03-19 | 2024-03-23 | 75% | Afreen
12 | S2 | 02. Appointment Management | 02.02 | Send Automated Reminders | Deploy the automated appointment reminder feature to the production environment | 2024-03-19 | 2024-03-23 | 75% | Vinay
13 | S2 | 02. Appointment Management | 02.02 | Send Automated Reminders | Monitor the performance of automated appointment reminders, including delivery rates and patient responses | 2024-03-19 | 2024-03-23 | 75% | Balu Venkat
14 | S2 | 02. Appointment Management | 02.02 | Send Automated Reminders | Conduct comprehensive testing to validate the accuracy and reliability of automated appointment reminder functionality | 2024-03-19 | 2024-03-23 | 75% | Naresh
15 | S2 | 02. Appointment Management | 02.02 | Send Automated Reminders | Design a database schema to store appointment reminder settings, patient contact information, and reminder delivery logs | 2024-03-19 | 2024-03-23 | 75% | Venkat Reddy
16 | S2 | 02. Appointment Management | 02.03 | Handling Cancelling and Rescheduling | Develop backend logic to handle appointment cancellation requests initiated by patients | 2024-03-24 | 2024-03-28 | 75% | Vinay
17 | S2 | 02. Appointment Management | 02.03 | Handling Cancelling and Rescheduling | Develop backend logic to handle appointment rescheduling requests initiated by patients | 2024-03-24 | 2024-03-28 | 75% | Likith
18 | S2 | 02. Appointment Management | 02.03 | Handling Cancelling and Rescheduling | Implement validation checks to ensure that cancellation and rescheduling requests meet predefined criteria (e.g., cancellation deadlines, availability of rescheduled time slots) | 2024-03-24 | 2024-03-28 | 75% | Surekha
19 | S2 | 02. Appointment Management | 02.03 | Handling Cancelling and Rescheduling | Develop functionality to notify healthcare providers of appointment cancellations and rescheduling requests | 2024-03-24 | 2024-03-28 | 75% | Afreen
20 | S2 | 02. Appointment Management | 02.03 | Handling Cancelling and Rescheduling | Verify that a patient can successfully cancel a scheduled appointment | 2024-03-24 | 2024-03-28 | 75% | Balu Venkat
21 | S2 | 02. Appointment Management | 02.03 | Handling Cancelling and Rescheduling | Verify that a patient can successfully reschedule a scheduled appointment | 2024-03-24 | 2024-03-28 | 75% | Naresh
22 | S2 | 02. Appointment Management | 02.03 | Handling Cancelling and Rescheduling | Crosscut: Excception Handling: Unable to cancel or reschedule the appointment | 2024-03-24 | 2024-03-28 | 75% | Surekha
23 | S2 | 02. Appointment Management | 02.03 | Handling Cancelling and Rescheduling | Verify that patients receive notification of appointment cancellation and rescheduling | 2024-03-24 | 2024-03-28 | 75% | Balu Venkat
24 | S2 | 03. Payment | 03.01 | Implement Secure Payment gateway and User Authentication | Develop functionality to integrate the payment gateway into the healthcare app | 2024-03-29 | 2024-04-02 | 100% | Surekha
25 | S2 | 03. Payment | 03.01 | Implement Secure Payment gateway and User Authentication | Implement secure communication protocols to ensure data encryption during payment transactions | 2024-03-29 | 2024-04-02 | 100% | Vinay
26 | S2 | 03. Payment | 03.01 | Implement Secure Payment gateway and User Authentication | Conduct integration testing to ensure seamless integration of the payment gateway into the website | 2024-03-29 | 2024-04-02 | 100% | Balu Venkat
27 | S2 | 03. Payment | 03.01 | Implement Secure Payment gateway and User Authentication | Verify that payment-related data is transmitted securely and that sensitive information is not exposed during transactions | 2024-03-29 | 2024-04-02 | 100% | Naresh
28 | S2 | 03. Payment | 03.01 | Implement Secure Payment gateway and User Authentication | Define tables, fields, and relationships in the database schema to support user authentication, user profiles, session management, and payment transactions | 2024-03-29 | 2024-04-02 | 100% | Arjun Reddy
29 | S2 | 03. Payment | 03.01 | Implement Secure Payment gateway and User Authentication | Crosscuts: FV - Field Validation, Check the account details validation | 2024-03-29 | 2024-04-02 | 100% | Vinay
30 | S2 | 03. Payment | 03.01 | Implement Secure Payment gateway and User Authentication | Conduct testing of the user authentication system to validate its security and functionality. | 2024-03-29 | 2024-04-02 | 100% | Naresh
31 | S2 | 03. Payment | 03.02 | Generate Receipts | Implement logic to calculate the total costs of healthcare services rendered, including consultation fees, procedure costs, medication expenses, and any applicable taxes or discounts | 2024-04-03 | 2024-04-06 | 100% | Vinay
32 | S2 | 03. Payment | 03.02 | Generate Receipts | Implement functionality to enable receipt delivery options, such as downloading the receipt from the healthcare app, sending the receipt via email to the patient, or providing a printed copy upon request | 2024-04-03 | 2024-04-06 | 100% | Likith
33 | S2 | 03. Payment | 03.02 | Generate Receipts | CrossCut: Exception Handling: Unable to Generate the receipts | 2024-04-03 | 2024-04-06 | 100% | Afreen
34 | S2 | 03. Payment | 03.02 | Generate Receipts | Incorporate payment information into the receipt document, including details of payment methods used (e.g., credit card, insurance), payment amounts, transaction dates, and payment confirmation numbers | 2024-04-03 | 2024-04-06 | 100% | Afreen
35 | S2 | 03. Payment | 03.02 | Generate Receipts | Test that a receipt is generated and displayed/downloaded upon the completion of a successful transaction | 2024-04-03 | 2024-04-06 | 100% | Balu Venkat
36 | S2 | 03. Payment | 03.03 | Manage Subscriptions | Implement Subscription Management Backend Logic | 2024-04-07 | 2024-04-09 | 100% | Vinay
37 | S2 | 03. Payment | 03.03 | Manage Subscriptions | Implement Subscription Modification Feature | 2024-04-07 | 2024-04-09 | 100% | Likith
38 | S2 | 03. Payment | 03.03 | Manage Subscriptions | Implement Subscription Cancellation Feature | 2024-04-07 | 2024-04-09 | 100% | Surekha
39 | S2 | 03. Payment | 03.03 | Manage Subscriptions | Test that users can modify their existing subscriptions | 2024-04-07 | 2024-04-09 | 100% | Naresh

## Sprint 3
Task # | Sprint | Module Name | RCT.Id | Core Feature | Task Description | Start Date | End Date | % Progress | Task Owner
1 | S3 | Send Automated Payment Remainders | 3.04 | Payment | Configure automated payment reminder schedules | 2024-04-10 | 2024-04-16 | 100% | Likith
2 | S3 | Send Automated Payment Remainders | 3.04 | Payment | Implement backend logic to identify overdue payments and trigger reminder notifications accordingly | 2024-04-10 | 2024-04-16 | 100% | Vinay
3 | S3 | Send Automated Payment Remainders | 3.04 | Payment | Ensure that reminders are sent only to users with pending payments and exclude users with cleared balances | 2024-04-10 | 2024-04-16 | 100% | Naresh
4 | S3 | Send Automated Payment Remainders | 3.04 | Payment | Verify that the reminder content includes relevant payment details | 2024-04-10 | 2024-04-16 | 100% | Balu Venkat
5 | S3 | Send Automated Payment Remainders | 3.04 | Payment | Crosscut: Connectivity: establish reliable connectivity between the payment reminder service and external systems | 2024-04-10 | 2024-04-16 | 100% | Surekha
6 | S3 | Send Automated Payment Remainders | 3.04 | Payment | Check the status of the delivered reminder | 2024-04-10 | 2024-04-16 | 100% | Naresh
7 | S3 | Display Advertisements | 4.01 | Advertising | Implement UI components (e.g., ad banners, sidebars) for displaying advertisements | 2024-04-17 | 2024-04-23 | 100% | Surekha
8 | S3 | Display Advertisements | 4.01 | Advertising | Define ad placement strategies within the website content section | 2024-04-17 | 2024-04-23 | 100% | Afreen
9 | S3 | Display Advertisements | 4.01 | Advertising | Customize ad layouts and formats to match the app's design guidelines and aesthetics, ensuring a seamless user experience | 2024-04-17 | 2024-04-23 | 100% | Likith
10 | S3 | Display Advertisements | 4.01 | Advertising | Verify that ads are displayed correctly within designated website sections | 2024-04-17 | 2024-04-23 | 100% | Balu Venkat
11 | S3 | Display Advertisements | 4.01 | Advertising | Crosscut: ET-Ex - External Entitlements User the advertisements are visible to user only if they are logged in | 2024-04-17 | 2024-04-23 | 100% | Vinay
12 | S3 | Handle Payments Queries | 5.03 | Customer Support | Implement recurring billing features and automated notifications for subscription renewals and payment reminders | 2024-04-24 | 2024-04-30 | 100% | Likith
13 | S3 | Handle Payments Queries | 5.03 | Customer Support | Provide support to users regarding payment-related inquiries, refund requests, and billing | 2024-04-24 | 2024-04-30 | 100% | Vinay
14 | S3 | Handle Payments Queries | 5.03 | Customer Support | Enable customer support agents to access payment details and transaction history seamlessly during support interactions | 2024-04-24 | 2024-04-30 | 100% | Surekha
15 | S3 | Handle Payments Queries | 5.03 | Customer Support | Generate an invoice for a completed transaction and verify that the invoice contains accurate details | 2024-04-24 | 2024-04-30 | 100% | Balu Venkat
16 | S3 | Handle Payments Queries | 5.03 | Customer Support | Crosscuts: FV - Field Validation, Check the email address validation | 2024-04-24 | 2024-04-30 | 100% | Afreen
17 | S3 | Handle Payments Queries | 5.03 | Customer Support | Test refund process by initiating a refund request and verifying that the refund is processed correctly and reflected in the user's payment history | 2024-04-24 | 2024-04-30 | 100% | Naresh
18 | S3 | Handle Feedback and Queries | 5.04 | Customer Support | Implement user-friendly interfaces for submitting feedback, queries, and support requests within the app | 2024-05-01 | 2024-05-06 | 100% | Surekha
19 | S3 | Handle Feedback and Queries | 5.04 | Customer Support | Track the status and progress of each feedback or query | 2024-05-01 | 2024-05-06 | 100% | Vinay
20 | S3 | Handle Feedback and Queries | 5.04 | Customer Support | Enable support agents to access relevant customer information and query history during interactions | 2024-05-01 | 2024-05-06 | 100% | Likith
21 | S3 | Handle Feedback and Queries | 5.04 | Customer Support | Implement user satisfaction surveys or ratings to gather feedback on support interactions and service quality | 2024-05-01 | 2024-05-06 | 100% | Afreen
22 | S3 | Handle Feedback and Queries | 5.04 | Customer Support | Verify that users can submit feedback with required details | 2024-05-01 | 2024-05-06 | 100% | Balu Venkat
23 | S3 | Handle Feedback and Queries | 5.04 | Customer Support | Track the progress of a query from submission to resolution and verify that status updates are reflected accurately | 2024-05-01 | 2024-05-06 | 100% | Naresh
24 | S3 | Handle Feedback and Queries | 5.04 | Customer Support | Crosscuts: FV - Field Validation, Check the email address validation | 2024-05-01 | 2024-05-06 | 100% | Vinay