## Sheet1
Module | Title | As a/an | I want to... | So that I can... | Sprint | Story | Story Constraints | Story Exceptions
01. User Management | 01.01 Establish User Access Control | Guest user,Product Owner | create a user account | access and use the application's features | S1 | 4 | User must provide a valid email address | Application displays an error message if invalid or duplicate email/ password provided
| 01.02 Implement Secure Authentication | Guest User, Registered User,Product Owner | secure authentication system implemented | can login to my account safely | S1 | 4 | Support 2-factor authentication via email/SMS | Email user if account is login from a new devices
| 01.03 Manage Data | Guest User, Registered User,Product Owner Healthcare Providers, Database Administrator 1 & Database Administrator 2 | be able to properly manage data in the system | oversee and control data storage, policies, and procedures | S1 | 4 | Users can only access data they have permissions for | In case of unexpected errors during data management operations, the system should provide guidance
| 01.04 Manage Account Recovery and Reset | Guest User, Registered User,Product Owner | securely recover or reset my lost or forgotten account credentials | regain access to my account | S1 | 4 | User must provide registered email or phone number to receive reset link | Notify user if account is locked after too many invalid reset attempts
| 01.05 Send User Notifications |  | receive relevant notifications. | be informed of important activities, changes or events related to my usage | S1 | 4
02. Appointment Management | 02.01 Schedule Appointments | Registered User,Product Owner | be able to easily schedule, reschedule | get confirmation of the date, time, location, doctor and other details | TBD | 4
| 02.02 Send Automated Reminders |  | manage automatic reminders to receive through various providers. | send reminders to patients about upcoming appointments and remind providers to follow up on test results | TBD | 2
| 02.03 Handle Cancellations and Rescheduling | Registered User, Product Owner,Healthcare providers & Health Information Technologist | cancel or reschedule my appointment | notify provider and update the appointment details | TBD | 2 | Users should have the option to cancel or reschedule appointments and notify the provider or relevant staff member immediately upon the cancellation or rescheduling of an appointment
| 02.04 Manage Patient History and Notes | Registered users,Product Owner, Database Administrator 2 | access to patient history and visit notes during appointment | provide relevant information for healthcare providers to prepare for appointments. | TBD | 4 | The system should provide a secure and user-friendly interface for accessing patient history and visit notes
| 02.05 Facilitate Patient Check-in | Product Owner,Healtcare providers & Health Information Technologist | be able to easily check-in for my scheduled appointment | notify staff of my arrival without waiting in long lines | TBD | 4 | Check-in functionality available 24/7 | Send appointment delay notification
03. Payment | 03.01 Integrate Secure Payment Gateway and User Authentication | Registered User,Product Owner,Healthcare Information Technologist & Financial Analyst | make payments seamlessly and securely, utilizing user-friendly authentication methods, ensuring my financial transactions are protected. |  | TBD | 4 | The authentication process for payments should be user-friendly, offering options such as biometric authentication (fingerprint, facial recognition), two-factor authentication (2FA), or secure one-time passwords (OTPs). | If a payment transaction fails due to technical issues or connectivity problems, the system should provide clear error messages and instructions for resolving the issue or attempting the payment again.
| 03.02 Generate Invoices | Product Owner,Database Administrator 2, Healthcare Information Technologist & Financial Analyst | access and download invoices detailing transactions | understand what costs I am being billed | TBD | 4 | The system should provide a user-friendly interface for accessing and managing invoices, accessible to both registered users and guest users. | If there are technical issues preventing users from accessing or downloading their invoices, the system should provide alternative methods for retrieving the necessary information, such as contacting customer support or requesting the invoices via email.
| 03.03 Manage Subscriptions | Registered User,Product Owner,Database Administrator 2, Healthcare Information Technologist & Financial Analyst | manage and customize my healthcare service subscriptions | easily access the services I require | TBD | 4 | Users should have the ability to view their current subscriptions, including details such as service type, subscription duration, and associated costs. | If a user attempts to modify their subscription during a billing cycle, the system should prorate the charges or refunds accordingly to ensure fair and accurate billing.
| 03.04 Send Automated Payment Reminders |  | receive timely reminders for upcoming payments | ensure my payments are made on time and avoid any potential disruptions | TBD | 4 | Reminders should clearly state due amount and due date | If user has previously declined reminders, discontinue sending
| 03.05 Handle Payment transactions | Registered User,Product Owner,Database Administrator 2, Healthcare Information Technologist & Financial Analyst (update in ET also) | able to view all transaction history related to my healthcare services | easily track and manage my payments | TBD | 4 | Transaction history showing payments, refunds, adjustments etc should be available for at least past 1 years | Allow users to report disputes on specific transactions
04. Advertising | 04.01 Display Advertisements | Product Owner,Digital Marketing Specialist | view advertisements promoted on the website to access various content | stay informed about relevant products or services | TBD | 4 | Ads must be relevant to site content and user context | If user has purchased premium ad-free subscription, do not show ads
| 04.02 Modify Updates | Product Owner,Digital Marketing Specialist | tailor the promotional content I receive | get relevant updates and offers that interest me | TBD | 3
| 04.03 Delete Expired or Non-Engaging Content | Product Owner,Digital Marketing Specialist | regularly review and remove expired or non-engaging content | maintain a relevant and engaging website for users | TBD | 2
| 04.04 Ad Scheduling | Product Owner,Digital Marketing Specialist | schedule when my ads will be displayed | optimize visibility during key dates, times, events | TBD | 3
| 04.05 Performance Analytics | Digital Marketing Specialist | prepare detailed analytics on my ad campaigns' performance | optimize towards key metrics and identify trends | TBD | 3
05. Customer Support | 05.01 Handle User Authentication Challenges | Guest User, Registered User,Product Owner, Healthcare Information Technologist & Customer Success Manager | easily contact customer support for authentication issues | get help with login, password, or account problems | TBD | 4 | Multiple communication channels - email, in-app chat, phone | Display estimated response times if support contact volume is high
| 05.02 Provide Appointment Guidance | Product Owner,Customer Success Manager | provide appointment guidance by offering support-related emails, helpline numbers, and step-by-step video tutorials | easily navigate the booking process and access necessary assistance when needed | TBD | 3
| 05.03 Handle Payments Queries | Registered User,Product Owner,Healthcare Information Technologist, Financial Analyst & Customer Success Manager | be able to inquire about my payments and billing | get answers to any questions | TBD | 4
| 05.04 Handle Feedback and Queries | Product Owner,Guest User, Registered User & Customer Success Manager | be able to provide feedback and ask questions | get prompt resolutions and assistance from customer support. | TBD | 4 | The feedback submission process should be straightforward, allowing users to provide relevant details and context for their feedback or inquiry.