## Road Map
Healthify PORTAL
|  |  | SPRINT 1 | SPRINT 2 | SPRINT 3
Application Modules | Feature Backlog | Story Points | SPRINT1 - 03/12/2024 | SPRINT2 - 04/09/2024 | SPRINT3 - 05/07/2024
01. User Management | 01.01 Establish User Access Control | 4 | x
| 01.02 Implement Secure Authentication | 4 | x
| 01.03 Manage Data | 4 | x
| 01.04 Manage Account Recovery and Reset | 4 | x
| 01.05 Send User Notifications | 4 | x
02. Appointment Management | 02.01 Schedule Appointments | 4 |  | x
| 02.02 Send Automated Reminders | 2 |  | x
| 02.03 Handle Cancellations and Rescheduling | 2 |  | x
| 02.04 Manage Patient History and Notes | 4
| 02.05 Facilitate Patient Check-in | 4
03.Payment | 03.01 Integrate Secure Payment Gateway and User Authentication | 4 |  | x
| 03.02 Generate Invoices | 4 |  | x
| 03.03 Manage Subscriptions | 4 |  | x
| 03.04 Send Automated Payment Reminders | 5 |  |  | x
| 03.05 Handle Payment transactions History | 4
04. Advertising | 04.01 Display Advertisements | 5 |  |  | x
| 04.02 Modify Updates/Promotions | 3
| 04.03 Delete Expired or Non-Engaging Content | 2
| 04.03 Delete Expired or Non-Engaging Content | 2
| 04.04 Ad Scheduling | 3
| 04.05 Performance Analytics | 3
05. Customer Support | 05.01 Handle User Authentication Challenges | 4
| 05.02 Provide Appointment Guidance | 3
| 05.03 Handle Payments | 5 |  |  | x
| 05.04 Handle Feedback and Queries | 5 |  |  | x
|  | VELOCITY: | 20 | 20 | 20